## TIME MANAGEMENT Gantt Chart
TIME MANAGEMENT GANTT CHART TEMPLATE
[ Project Name ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning | 2022-01-16 | 2022-01-21 | 6
Wireframes | 2022-01-22 | 2022-01-23 | 2
Image Sourcing | 2022-01-22 | 2022-01-30 | 9
Graphics | 2022-01-27 | 2022-01-29 | 3
Design | 2022-01-28 | 2022-02-04 | 8
Search Incorporation | 2022-02-05 | 2022-02-09 | 5
Standards | 2022-01-28 | 2022-02-05 | 9
Legal | 2022-02-04 | 2022-02-06 | 3
Testing | 2022-02-07 | 2022-02-10 | 4
Optimization | 2022-02-09 | 2022-02-12 | 4
Platform Adaptation | 2022-02-11 | 2022-02-14 | 4
App Development | 2022-02-15 | 2022-02-17 | 3
Marketing | 2022-01-28 | 2022-02-05 | 9
Rollout | 2022-02-04 | 2022-02-06 | 3
Documentation | 2022-02-07 | 2022-02-10 | 4
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description
MILESTONE 5:
00/00/00
Brief Description
MILESTONE 4:
00/00/00
Brief Description

## TIME MANAGEME Gantt Chart BLANK
TIME MANAGEMENT GANTT CHART TEMPLATE
[ Thyroid Detection System ]
TASK NAME | START DATE | END DATE | DURATION (days)
Requirement Gathering & Analysis | 2021-10-10 | 2021-10-13 | 4
System Design & Architecture | 2021-10-13 | 2021-10-20 | 8
UI/UX Design & Mockups | 2021-10-20 | 2021-10-23 | 4
Project Plan & Schedule | 2021-10-23 | 2021-10-26 | 4
Develop the System & Rules | 2021-10-26 | 2021-11-06 | 12
Implement User Interface | 2021-11-01 | 2021-11-10 | 10
Choose & Research AI Algorithm | 2021-11-03 | 2021-11-06 | 4
Develop & Train AI Model | 2021-11-06 | 2021-11-25 | 20
Integrate AI with the System | 2021-11-25 | 2021-12-05 | 11
Develop Unit Test | 2021-12-06 | 2021-12-12 | 7
Design & Implement AI Performance Test | 2021-12-11 | 2021-12-18 | 8
Conduct User Testing & Gather Feedback | 2021-12-15 | 2021-12-18 | 4
Fix Bugs & Address User Feedback | 2021-12-20 | 2021-12-27 | 8
Final Testing & Quality Assurance | 2021-12-25 | 2021-12-29 | 5
Documentation & User Manual Preparation | 2021-12-28 | 2022-01-01 | 5
Deployment & Release on chosen platform | 2021-12-29 | 2022-01-05 | 8
Project Reports & Presentation | 2021-10-30 | 2022-01-12 | 75
Team Evaluation & Lesson Learned | 2022-01-01 | 2022-01-04 | 4
MILESTONE 1:
10/10/23
PLANNING & DESIGN
MILESTONE 2:
10/26/23
DEVELOPMENT
MILESTONE 3:
12/20/23
TESTING & DEPLOYMENT
MILESTONE 4:
10/30/23
PROJECT COMPLETION & REVIEW
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.