## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER | KEE CHIN YEW
COMPANY NAME | WORKSHOP2 - BITI
DATE | 2023-07-06 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Planning & Design
1.1 | Requirement Gathering & Analysis | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-10-10 | 2023-10-13 | 3 | 100%
1.2 | System Design & Architecture | SHARIZAD, KEE CHIN YEW | 2023-10-13 | 2023-10-20 | 7 | 100%
1.3 | UI/UX Design & Mockups | DEVESHWER | 2023-10-20 | 2023-10-23 | 3 | 100%
1.4 | Project Plan & Schedule | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-10-23 | 2023-10-26 | 3 | 100%
2 | Development
2.1 | Develop game engine & rules | DEVESHWER | 2023-10-26 | 2023-11-06 | 11 | 100%
2.2 | Implement user interface & graphics | DEVESHWER | 2023-11-01 | 2023-11-10 | 9 | 100%
2.3 | Choose & research AI algorithm | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-11-03 | 2023-11-06 | 3 | 100%
2.4 | Develop & train AI model | KEE CHIN YEW | 2023-11-06 | 2023-11-25 | 19 | 100%
2.5 | Integrate AI with game engine | KEE CHIN YEW | 2023-11-25 | 2023-12-05 | 10 | 100%
2.6 | Develop unit tests for game logic | DEVESHWER | 2023-12-06 | 2023-12-12 | 6 | 100%
2.7 | Design & implement AI performance tests | KEE CHIN YEW | 2023-12-11 | 2023-12-18 | 7 | 100%
2.8 | Conduct user testing & gather feedback | DEVESHWER | 2023-12-15 | 2023-12-18 | 3 | 100%
3 | Testing & Deployment
3.1 | Fix bugs & address user feedback | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-12-20 | 2023-12-27 | 7 | 80%
3.2 | Final testing & quality assurance | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-12-25 | 2023-12-29 | 4 | 0%
3.3 | Documentation & user manual preparation | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-12-28 | 2024-01-01 | 4 | 60% | [31 empty] | 2023-12-29
3.4 | Deployment & release on chosen platform | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-12-29 | 2024-01-05 | 7 | 60%
4 | Project Completion & Review
4.1 | Project reports & presentation | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2023-10-30 | 2024-01-12 | 74 | 70%
4.2 | Team evaluation & lessons learned | SHARIZAD, KEE CHIN YEW, DEVESHWER | 2024-01-01 | 2024-01-04 | 3 | 70%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%